## Sheet1
Waterfall Gantt Chart Template
Project Title: | Yosemite |  | Start Date: |  | 2025-01-06
Project Manager: | Long Nguyen |  | Estimated Completion Date: |  | 2025-03-20
TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[5 empty] | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F
Storefront on the platform | bar: WEEK 9 M to WEEK 12 F
Kickoff Meeting | Moe, Lou, Aliyah | 2025-01-06 | 2025-01-06 | 1 | bar: WEEK 1 M
Build storefront | Aliyah, Moe | 2025-01-07 | 2025-01-20 | 10 | bar: WEEK 1 T to WEEK 3 M
Status Report | Aliyah, Moe | 2025-01-21 | 2025-01-21 | 1 | bar: WEEK 3 T
Input Inventory Data | Moe | 2025-01-22 | 2025-01-29 | 6 | bar: WEEK 3 W to WEEK 4 W
Status Report | Moe | 2025-01-30 | 2025-01-30 | 1 | bar: WEEK 4 Tr
Train Stefano’s on platform | Moe | 2025-01-31 | 2025-02-03 | 2 | bar: WEEK 4 F to WEEK 5 M
Documenting knowledge | Moe, Lou, Aliyah | 2025-02-04 | 2025-02-05 | 2 | bar: WEEK 5 T to WEEK 5 W
Social media integration | bar: WEEK 9 M to WEEK 12 F
Kickoff Meeting | Aliyah, Taylor | 2025-02-06 | 2025-02-06 | 1 | bar: WEEK 5 W
Create social media channels | Taylor | 2025-02-07 | 2025-02-12 | 4 | bar: WEEK 5 Tr to WEEK 6 T
Status Report | Taylor | 2025-02-13 | 2025-02-13 | 1 | bar: WEEK 6 W
Build social media integration | Aliyah | 2025-02-14 | 2025-02-19 | 4 | bar: WEEK 6 Tr to WEEK 7 T
Status Report | Aliyah | 2025-02-20 | 2025-02-20 | 1 | bar: WEEK 7 W
Train Stefano’s on social media use | Taylor | 2025-02-21 | 2025-02-24 | 2 | bar: WEEK 7 Tr to WEEK 7 F
Documenting knowledge | Aliyah, Taylor | 2025-02-25 | 2025-02-26 | 2 | bar: WEEK 8 M to WEEK 8 T
Recommendation engine | bar: WEEK 9 M to WEEK 12 F
Kickoff Meeting | Aliyah, Me, Moe | 2025-02-27 | 2025-02-27 | 1 | bar: WEEK 8 W
Build recommendation engine | Aliyah | 2025-02-28 | 2025-03-06 | 5 | bar: WEEK 8 Tr to WEEK 9 W
Status Report | Aliyah | 2025-03-07 | 2025-03-09 | 1 | bar: WEEK 9 Tr
Create Automated Sales Report | Moe | 2025-03-10 | 2025-03-12 | 3 | bar: WEEK 9 F to WEEK 10 M
Status Report | Moe | 2025-03-13 | 2025-03-13 | 1 | bar: WEEK 10 T
Engage stakeholders | Me | 2025-03-14 | 2025-03-17 | 2 | bar: WEEK 10 W to WEEK 10 Tr
Documenting knowledge | Aliyah, Me, Moe | 2025-03-18 | 2025-03-19 | 2 | bar: WEEK 10 F to WEEK 11 M
Closure meeting | Me | 2025-03-20 | 2025-03-20 | 1 | bar: WEEK 11 T
Formulas:
Start Date: = WORKDAY([START DATE],[DURATION])-1
START DATE = WORKDAY([Start Date:, row above],1)